## Sheet1
COMPSYS301
Design Meeting: Group 14
Date | Wednesday 26 August 2026
Time | 3:00 pm - 4:00 pm
Apologies | None. All group members present (Abdur, Lucas, Harold, Ross).
Goals, Objectives, Discussion Items | • Review the path-finding work and decide whether to keep a second algorithm as a backup. • Review Ross's completed PCB design as a whole team and check it for problems. • Go over the repeated experiments validating the sensor and the filter design. • Plan the demo circuit.
Achievements, Conclusions, Action Points | Achievements • Harold and Lucas agreed to keep Dijkstra as a backup path-finding option. • Ross finished the PCB design and presented it to the entire team. • Harold redid the experiments to validate the sensor and the filter design. • The whole team went over the PCB design together and found no problems with it. Conclusions • BFS stays as the main path-finding algorithm. Dijkstra will only be implemented if there is time left over. • The PCB design is confirmed by the team and can move forward. • The repeated experiments support the sensor and filter design. Action Points • Harold and Lucas: keep working on BFS, and start Dijkstra only if the schedule allows it. • Ross and Abdur: work on the demo circuit. • All: raise any further PCB issues as soon as they are found.
Next Meeting | Wednesday 2 September 2026, 3:00 pm - 4:00 pm