## 2026-07-29
COMPSYS301
Design Meeting: Group 14
Date | Wednesday 29 July 2026
Time | Start: 15:00 Finish: 15:56 Place: MDLS Lab, E&I 1/2
Apologies | Present: Harold, Lucas, Abdur, Ross Apologies: None
Goals, Objectives, Discussion Items | GOAL Plan Hardware Task 2. Only agenda item. DISCUSSED 1. Task 2 goal: speed vs voltage curve for one motor. PSoC PWM sets the voltage, MC33926 supplies the current, encoder measures speed. 2. Build order agreed: PWM first, then MC33926 signal mods, then drive the motor, then speed sensing, then the sweep. 3. Drive mode: locked anti-phase. One PWM wire. 50 % duty = 0 V. 4. PWM Period = 100 for 1 % resolution. One fixed frequency. 5. IN1 direct, IN2 inverted. EN/D1/D2 hard-wired per Tables 1 and 5. 6. Encoder is on the motor shaft. 3 pulses x 19:1 gearbox = 57 per output rotation, 228 in 4x mode. 7. Speed from QuadDecoder counts over a fixed timer interval, calculated in the ISR. 8. QuadDecoder: 16 bit, 4x mode, no index, glitch filter on. Output via USBUART to PuTTY. 9. Sweep -V to +V in 0.5 V steps, automatic in C, plotted in MATLAB. 10. Battery voltage measured three times: stopped, full speed, after sweep. 11. Robot stays on the platform. TA checks wiring before first power-up.
Achievements, Conclusions, Action Points | DONE 1. Read the brief together. 2. Agreed drive mode, build order and work split. 3. Worked out the encoder count maths. ACTIONS 1. All: read brief, MC33926 Tables 1 and 5, motor and encoder specs. Fri 31 July. 2. Lucas: build PWM, check frequency and duty on scope. Fri 31 July. 3. Harold: work out IN1/IN2 logic and EN/D1/D2 wiring. Fri 31 July. 4. Harold + Lucas: verify 50 % duty signal, J18/J13 disconnected. Mon 3 Aug. 5. Abdur: add QuadDecoder, Timer, USBUART. Speed in RPM to PuTTY. Tue 4 Aug. 6. Ross: measure max encoder frequency at 100 % duty. Set timer period. Tue 4 Aug. 7. Ross: write the automatic sweep. Tue 4 Aug. 8. Abdur: record battery voltage at the three points. Tue 4 Aug. 9. All: one brief question each, written up. Tue 4 Aug. 10. Lucas: book robot and platform. Thu 30 July.
Next Meeting | Wednesday 5 August 2026, 15:00 MDLS Lab, E&I 1/2 Update on actions. First speed vs voltage plot.