## Sheet1
COMPSYS301
Design Meeting: Group 14
Date | 2026-08-05
Time | 3:00 pm to 4:00 pm (1 hour)
Apologies | None. All group members present: Abdur, Lucas, Harold, Ross.
Goals, Objectives, Discussion Items | Software (path finding) • Abdur and Lucas presented their exploration of depth-first search (DFS) for the path-finding task. • Harold discussed it with them and compared DFS against breadth-first search (BFS). • Debated which algorithm is more feasible for our robot, and whether to keep the DFS work already started. Hardware • Ross reported on the completion of Hardware Task 2. • Discussed the plan for testing the shunt resistor used with the phototransistor.
Achievements, Conclusions, Action Points | Achievements • Abdur and Lucas completed their exploration of DFS. • Ross wrapped up Hardware Task 2. Conclusions • BFS looks more feasible than DFS, but we agreed to implement both and test them next week before committing. Action points • Abdur, Lucas, Harold: implement DFS and BFS, test both next week. • Ross: begin testing the shunt resistor used with the phototransistor.
Next Meeting | Week beginning 10 August 2026, date and time to be confirmed.