## Sheet1
COMPSYS301
Design Meeting: Group 14
Date | Wednesday 12 August 2026
Time | 3:00 pm - 4:00 pm
Apologies | None. All group members present (Abdur, Lucas, Harold, Ross).
Goals, Objectives, Discussion Items | • Review the two path-finding algorithms assigned at the previous meeting: depth-first search (DFS) and breadth-first search (BFS). • Discuss how to test the algorithms against the visualisation tools provided in MATLAB. • Compare DFS and BFS to decide which is suitable for the navigation task. • Review Ross's shunt resistor design and the results of his testing.
Achievements, Conclusions, Action Points | Achievements • Abdur implemented the DFS algorithm. • Lucas implemented the BFS algorithm. • Harold created a Python adapter so both algorithms can be tested with the MATLAB visualisation tools provided, and modularised the two algorithms so they share a common interface. • Ross completed the shunt resistor testing and discussed his design with the rest of the group. Conclusions • DFS is not viable for this application because it cannot find the shortest path. • BFS is carried forward as the path-finding algorithm. Action Points • Abdur and Lucas: continue the path-finding work on top of BFS. • Harold: keep the Python adapter and the module interface in step with any changes to BFS. • Ross: carry on with the shunt resistor design using the test results discussed.
Next Meeting | Wednesday 19 August 2026, 3:00 pm - 4:00 pm