## Sheet1
COMPSYS301
Design Meeting: Group 14
Date | Wednesday 19 August 2026
Time | 3:00 pm - 4:00 pm
Apologies | None. All group members present (Abdur, Lucas, Harold, Ross).
Goals, Objectives, Discussion Items | • Review the A* path-finding algorithm that Lucas explored after the previous meeting. • Decide whether to build on A* or prototype with BFS first. • Discuss the 60 Hz noise the sensors pick up from the projector and how to filter it out. • Agree on what has to be settled before PCB design can start.
Achievements, Conclusions, Action Points | Achievements • Lucas explored and implemented the A* algorithm, then explained it to the rest of the group. • Harold integrated A* into the test module. • Abdur and Ross started designing a filter to remove the 60 Hz noise coming from the projector. Conclusions • A* is more complex than the prototype needs at this stage, so BFS will be used for the first prototype. A* stays on the table and may replace it later. • PCB design can begin once the filter design is settled. Action Points • Lucas and Harold: build the prototype around BFS and keep the A* implementation in the test module so it can be swapped back in. • Abdur and Ross: finish the 60 Hz filter design. • All: move on to PCB design once the filter is confirmed.
Next Meeting | Wednesday 26 August 2026, 3:00 pm - 4:00 pm